## Sheet1
Eric Gan | Start | End | hours | job done
2012-11-25 | 10:25 | 11:20 | 1 | Wrote Animation from scratch; reviewed basic features of Tkinter on 15-112 website
2012-11-27 | 7:37 | 8:33 | 1 | Explored pygame, but realized that learning a new module at this stage was futile.
2012-11-28 | 9:20 | 10:53 | 1.5 | Wrote a good amount of Board. Tried to figure out how to implement jumping by looing at physics equations.
2012-11-28 | 5:00 | 6:02 | 1 | Met with Asa. Added some variables
2012-11-28 | 8:02 | 8:55 | 1 | Implemented more variables.
2012-11-29 | 11:25 | 12:17 | 1 | Started to draw the main interface. Looked into KeyPressed events on 15-112 website for smooth navigating
2012-11-29 | 11:02 | 0:44 | 1.75 | Got my rectangle moving left and right, and got portal to work. Next step, getting my thing to jump.
2012-11-30 | 1:13 | 1:48 | 0.5 | Tried to figure out how to get the canvas to "jump" by shifting the whole canvas/scroll view.
2012-11-30 | 2:00 | 2:30 | 0.5 | Got jump to "work" but not display correctly.
2012-11-30 | 9:30 | 11:18 | 2 | Got jump to work correctly.. Almost! Added falling blocks that disappear when they hit the ground. Tried to make moving smoother.
2012-11-30 | 1:33 | 2:18 | 0.75 | Got player to jump correctly after debugging! Now trying to figure out how to place blocks onto the floor (and collision detection)
2012-11-30 | 3:30 | 4:02 | 0.5 | Played some avalanche. Tried to get collision to work.
2012-12-01 | 3:00 | 3:30 | 0.5 | Attempted to program jumping and collision detection on things other than the floor, but did not work.
2012-12-01 | 1:03 | 1:24 | 0.5 | Tried to get jump to work on top of blocks.
2012-12-01 | 4:00 | 6:50 | 3 | Got my blocks to stack! Now working on jumping.
2012-12-01 | 7:56 | 9:30 | 1.5 | Got player to jump on blocks correctly! Still working on a bug where player falls through a block in mid-air after about 2 seconds…
2012-12-01 | 9:45 | 1:27 | 3.75 | Player now jumps on blocks correctly. Falls down correctly. Fixed annoying bug where player goes "inside" a block when L/R move is illegal.
2012-12-02 | 12:05 | 3:10 | 3 | Fixed top/town collision. Need to rewrite L/R collision. Still small bug for T/D collision that needs to be fixed. Banged head from time to time.
2012-12-02 | 3:30 | 5:06 | 1.5 | Realized a small bug with block stacking…and fixed it! Got top/bottom collision to work for the most part. L/R still problematic.
2012-12-02 | 11:30 | 12:25 | 0.75 | For the most part, fixed L/R movement. Still buggy though.
2012-12-03 | 2:00 | 2:56 | 1 | Lots of debugging… not much improvement.
2012-12-03 | 3:30 | 4:00 | 0.5 | Fixed L/R movement bug with a hack (unfortunately).
2012-12-04 | 2:15 | 2:45 | 0.5 | Added wall jumping. Noticed a new interesting (rare) bug….
2012-12-04 | 1:20 | 2:54 | 1.5 | Added general GUI stuff. Tried to fix wrap-around bug
2012-12-04 | 4:15 | 6:37 | 2.25 | Added Smash. Fixed (somewhat) wrap-around bug. Added a way to actually lose the game. Added water. Made a lose-game indicator. Also made instructions page.
2012-12-04 | 10:00 | 11:55 | 2 | Fixed some bugs. Generally still buggy, but playable now! Added Credits Page. Finishing Touches!
2012-12-05 | 4:32 | 6:34 | 2 | Added music using pygame; added death effect. Recorded video. Finishing touches.
| Total | 36.75